Assessment and Determination of Risk Mitigation Dimensions in Public Construction Projects. A case study in Ethiopian construction projects.

Wondimagegn Tadesse Borku1, Sahil Garg2   and Syed Zafar Shahid Tabish 3

1Ph. D Research Scholar, Department of Civil and Environmental Engineering, Indian Institute of Technology Delhi, New Delhi, India, E-mail:cez248704@civil.iitd.ac.in (Corresponding author).

2Assistant Professor, Department of Civil and Environmental Engineering, Indian Institute of Technology, New Delhi ,E-mail: gargsahail@civil.iitd .ac.in

3Professor of Practice, Department of Civil and Environmental Engineering, Indian Institute of Technology, New Delhi, India, E-mail: szstabish@civil.iitd.ac.in

Abstract:

Construction project risks are uncertain events that can positively or negatively affect project objectives. When risks are not properly managed from the initial stages, they can result in project failures, injuries, delays, disputes, cost overruns, and other adverse consequences. Ethiopian construction projects face significant challenges associated with these risks, highlighting the need for effective risk mitigation practices. Despite extensive research on construction risk identification and assessment, limited attention has been given to systematically determining risk mitigation dimensions for public construction projects in developing countries, particularly Ethiopia. To address this gap, this study aims to identify and analyze risk mitigation measures that can increase the likelihood of successful public construction projects. A detailed literature review was conducted to identify risk mitigation attributes for public construction projects. A total of 29 attributes were identified through the literature review and consolidated through interviews and pilot studies with construction industry professionals. A questionnaire containing the 29 attributes was distributed to various stakeholders, and 118 completed questionnaires were returned. The Relative Importance Index was used to rank the attributes, and principal component analysis (PCA) was performed to group the attributes into underlying dimensions. The five highest-ranked attributes were 1. on-time decision-making, 2. ensuring that construction teams have the necessary qualifications, abilities, and experience, 3. solving disputes efficiently, 4. transparent procurement and competitive tendering process, and 5. audit norms. The PCA results grouped the 29 attributes into five key risk mitigation dimensions: 1. pre-project planning dimensions, 2. project monitoring and controlling dimensions, 3. project-related dimensions, 4. inter-partner relationships dimensions, and 5. Project management skills. The findings provide a basis for proactively mitigating risks and addressing management-related challenges in Ethiopian public construction projects.

keywords: Construction project risk, public construction project, Risk mitigation measures, Relative importance index and Factor analysis

1.Introduction

The construction sector plays a vital role in a country’s development, quality of life, tourism, environmental sustainability, economic growth, and job creation (Fathi, 2024).Globally the sector accounts for 7.7% of total employment (Acolin et al., 2021).However, construction projects are exposed to various risks that, if not properly managed from the initial stages, can lead to financial losses, project failures, injuries, delays, disputes, cost overruns, and other adverse consequences (Cherkos & Asfaw, 2025; Ferede et al., 2021).

In construction projects, risk refers to an uncertain event that can have a positive or negative impact on project performance, while unmanaged risks remain a major concern for project success (Cherkos & Asfaw, 2025).

Delays, cost overruns, quality problems, and disputes in construction projects are primarily associated with project complexity, the nature of construction activities, stakeholder-related issues, technical risks, and funding problems (Alhammadi et al., 2025; Belihu et al., 2026; Gouda Mohamed et al., 2023; Hoque & Hasan, 2025) .These challenges are particularly evident in the Ethiopian construction sector, where project performance remains concerning. Reports on the Ethiopian construction industry have highlighted significant challenges related to the iron triangle(time, cost, and quality) as well as safety issues. For instance, only 8.25% of projects in Ethiopia were completed by their original targeted completion dates, whereas the remaining 91.75% experienced delays equivalent to 352% of their contractual time (Koshe & Jha, 2016).Similarly, (Dessa, 2003.) examined the performance of 15 completed projects in different regions of Ethiopia and found that delays in most projects ranged from 20.66% to 500% of the original contract duration. Cost increases exceeded 80% of the contractual sum. Furthermore, claims in large-scale construction projects in Ethiopia can reach millions of Ethiopian Birr and, in some cases, exceed 100% of the project cost costs (Dinku & Kahssay,2003). In addition, 38.3% of building construction employees experiencing an injury (Tadesse & Israel, 2016).

These findings indicate that limited attention has been given to risk mitigation in construction projects in Ethiopia, highlighting the need for further investigation. Therefore, to address this gap, this study aims to investigate the following research question: What risk mitigation measures can improve the performance of Ethiopian public construction projects in addressing challenges related to the iron triangle and disputes? To answer this question, the study aims to identify and analyze risk mitigation measures that can increase the likelihood of successful public construction projects.

2.Literature Review

Construction projects are unique, temporary, and complex, and, due to the characteristics of the construction industry, risks arise from several different sources (A Guide to the Project Management Body of Knowledge Third Edition (PMBOK ® Guide,2004.).Risk can be defined as the probability of an event and the consequence of loss associated with that event (Endris Yadeta, 2020). Given the inherent nature of the construction industry, risks cannot be completely avoided; however, their likelihood of occurrence and potential impacts can be minimized through effective risk management (Endris Yadeta, 2020).This is particularly important in public construction projects, where inadequate risk management can contribute to poor project performance in terms of time, cost, quality, and disputes.

Risk management is the process of risk identification, analysis, response, monitoring, and control throughout a project. The main goal of risk management is to increase the probability and impact of positive events and decrease the probability and impact of events adverse to the project(A Guide to the Project Management Body of Knowledge Third Edition (PMBOK ® Guide,2004.).Risk identification is the first step in the risk management process and involves determining the potential sources and root causes of risks (Szymański, 2017).Following risk identification and analysis, appropriate responses are required to reduce the potential consequences of identified risks. Risk mitigation involves reducing both the likelihood of occurrence and the potential impact of risks (Lin & Chen, 2021; Tang et al., 2007). Therefore, effective risk management requires not only identifying and classifying risks but also determining appropriate mitigation measures.

Construction risks are categorized into internal and external risks. External risks are beyond the control of project teams and. In contrast, internal risks arise from the specific nature of the project and events occurring within the control of the project organization (Endris Yadeta, 2020).According to the study by (Shibani et al., 2024) internal risks in large construction projects are associated with the management and control of project activities. These risks originate within the project organization and may involve the responsibilities of owners, architects, suppliers, designers, contractors, and subcontractors. Thus, both internal and external sources need to be considered when developing effective risk mitigation strategies for construction projects.

Previous studies have predominantly focused on identifying, classifying, ranking, and assessing the effects of internal and external risks on construction project performance. External risks have included natural, economic, social, environmental, political, and legal risks, whereas internal risks have included financial, contractual, logistics, construction, procurement, technical, and management risks (Chandra, 2015; Cherkos & Asfaw, 2025; Endris Yadeta, 2020; Gouda Mohamed et al., 2023; Gupta et al., 2025; Kivrak & Udan, 2023; Tessema et al., 2022; Yang et al., 2025; Zegeye & Darsa, 2024).These studies demonstrate that construction risks can substantially affect project performance. In Ethiopia, project performance has been particularly affected by  iron triangle(time, cost, and quality) as well as safety issues (Koshe & Jha, 2016; Dessa, 2010,Tadesse & Israel, 2016). Furthermore, when risks are not effectively managed from the initial stages of a project, they can result in injuries, delays, disputes and overrun cost (Ferede et al., 2021).

Although previous studies have provided valuable insights into construction risk identification, classification, and assessment, limited attention has been given to determining the dimensions of risk mitigation measures, particularly in public construction projects in developing countries. Most existing studies have emphasized the sources and effects of risks rather than systematically determining mitigation dimensions that can help reduce their likelihood and impact. To address this research gap, particularly in the context of Ethiopian public construction projects. Therefore, the present study focuses on determining the key dimensions of risk mitigation in public construction projects.

3. Research Methodology

The methodology flowchart is systematically presented in Figure 1 below.

Problem identification

Literature Review

Experts Discussions

First draft questionary development

Pilot survey

Based on expert discussions, the questionnaire was modified

Reliability test

Validation of questionnaire

Conclusions and recommendations

Results and Discussions

Questionnaires were distributed to the respondent’s respondents working in public construction projects.And collection of respo

Relative importance index

Data collection

Factor analysis

Figure1: Methodology flow chart

To achieve the objectives of this study, the research methodology consists of six steps, which include the following: Step 1: Attributes identification, Step 2: Preliminary study, Step 3: Data collection using a questionnaire survey, Step 4: Sampling size determination, Step 5: Calculation of Relative Importance Index and Step 6: Exploratory Factor Analysis

Step1: Attributes identification: - After an in-depth review of the literature and expert opinion, a set of variables that influence risk mitigation measures in public construction projects was identified. All identified attributes were listed in Table 1 below with their corresponding references .

Table 1:  Codes, Attributes and References

| Code | Attributes | References |
| --- | --- | --- |
| F2VAR28 | Adequate plan and specification | (Aragaw & Cherkos, 2025) |
| F2VAR60 | Detailed feasibility study before starting the project (Conducting a geological and climatic study) | Suggested by expert |
| F2VAR26 | Stakeholder engagement in projects | (Fathi, 2024) |
| F2VAR70 | Clear and precise goals (scope clarity) | (Aragaw & Cherkos, 2025) |
| F2VAR25 | Define clear responsibilities in the contract | (Aragaw & Cherkos, 2025; Tabish & Jha, 2012) |
| F2VAR24 | Allocating contingency for uncertainties | (Viswanathan et al., 2020) |
| F3VAR14 | Visiting the site regularly | (Maddah et al., 2026) |
| F3VAR18 | Regular quality control and quality assurance activities | (Sinesilassie et al., 2018) |
| F3VAR17 | Adequate communication among all project participants | (Tripathi & Jha, 2018) |
| F3VAR15 | Consideration of cultural and language factors in project site | Suggested by expert |
| F3VAR13 | Regular monitoring and feedback by top Management | (Sinesilassie et al., 2018) |
| F4VAR16 | Clear reporting system | (Cheng & Darsa, 2021) |
| F4VAR20 | Regular project updates | (Tabish & Jha, 2012) |
| F5VART2 | Transparent procurement and competitive tendering process | (Ababa, 2011; Fathi, 2024) |
| F1VAR46 | Ensuring construction teams have the necessary qualifications, abilities, and experience | (Yang et al., 2025) |
| F1VAR44 | Audit norms | (Ababa, 2011; Tabish & Jha, 2018) |
| F1VAR47 | Availability of resources (material, manpower, machinery and money) as planned throughout the project. | (Sinesilassie et al., 2018) |
| F1VAR45 | Timely land acquisition and appropriate compensation | (Fathi, 2024) |
| F5VAR31 | Good coordination between project participants | (Kineber et al., 2024; Tabish & Jha, 2012) |
| F1VAR40 | Flow of the information among parties | (Bakr, 2018) |
| F2VAR30 | Using new technological approaches | (Kineber et al., 2024) |
| F4VAR29 | Clients’ active enrollment and support | (Kineber et al., 2024) |
| F5VAR33 | Solving disputes efficiently | (Bakr, 2018) |
| F5VAR32 | Adequacy of the planning and control techniques | (Sinesilassie et al., 2018) |
| F4VAR27 | On-time decision-making | (Yang et al., 2025) |
| F1VAR39 | Project manager competency | (Tabish & Jha, 2012) |
| F1VAR38 | Commitment of all Project Participants | (Yang et al., 2025) |
| F1VAR43 | Appropriate risk allocation and risk-sharing | (Fathi, 2024) |
| F1VAR50 | Owners Competency | (Aragaw & Cherkos, 2025; Tabish & Jha, 2012) |

Step2: Preliminary study :- As shown in the methodology flowchart in Figure 1, the risk mitigation attributes listed in Table 1 were discussed in detail with three experts with more than 20 years of experience in construction projects to assess their suitability for projects. These experts were selected based on their extensive experience in executing construction projects and their availability. After two rounds of face-to-face discussions with each expert and a few recommendations, the experts concluded that the list of 29 attributes was generally suitable and that no further modifications were needed.

Step 3: Data collection using a questionnaire survey: Data was collected using a questionnaire survey. 200 questionnaires were distributed to industry experts working on public construction projects. A total of 118 complete responses were received. The questionnaire had two parts: part 1 covered respondents' details, such as education level and project experience. In part 2 of the questionnaire, participants were asked to rate the influence of the 29 attributes identified on the project's performance on a Likert scale from 1 (least impact) to 7 (extremely high impact). The respondent's background is explained in Table 2 below.

Table 2: Respondent’s background

| Position | Questionnaire |  | Education level |  |  |  | Experience(years) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Distributed | Valid Response | Diploma | B.Sc. | M.Sc. | Ph.D | 5-10 | 11-20 | Above 20 |
| Project engineer | 40 | 24 | 0 | 15 | 9 | 0 | 8 | 10 | 6 |
| Construction manager | 35 | 27 | 0 | 10 | 16 | 1 | 7 | 8 | 12 |
| Quantity Surveyor | 25 | 16 | 2 | 14 | 0 | 0 | 6 | 7 | 3 |
| Project Manager | 44 | 23 | 0 | 13 | 9 | 1 | 3 | 12 | 8 |
| Architect | 20 | 10 | 0 | 4 | 6 | 0 | 4 | 3 | 3 |
| Health and safety officer | 20 | 8 | 2 | 4 | 2 | 0 | 3 | 4 | 1 |
| Quality manager | 16 | 10 | 0 | 10 | 0 | 0 | 4 | 3 | 3 |
| Total | 200 | 118 | 4 | 70 | 42 | 2 | 35 | 47 | 36 |

Step 4: Sampling size determination:

The required size was determined using the formula(COCHRAN, 1977),expressed as:

n0=Z2⋅p⋅(1-p)e2                                                                                                           Eq.1                     
Where n0 is the required sample size, Z is the selected critical value of the desired confidence level, p is the estimated proportion of the infinite population (assumed as 0.5 to ensure maximum variability), and e is the acceptable margin of error. For a confidence level of 95% (z = 1.96), with q = 1-p = 0.5, and 90% precision(e=0.10),  the minimum number of respondents required is 97. The actual sample size (n=118) exceeds the requirement and is therefore considered sufficient for statistical and factor analyses (Hair et al., 2019) (Tripathi & Jha, 2018)

Step 5: Calculation of Relative Importance Index:

The relative importance index (RII) has been widely used in construction management studies(Chan & Kumaraswamy, 1997; Garg & Misra, 2021). In this study, the RII for each attribute was calculated using equation two.

RII=(Σw)A*N   ,0 ≤ RII ≤ 1  and    MS = (Σw)N                                                                                        Eq.2

Where, w = weighting given to each factor by the respondents and ranges from 1 to 7 (from least impact to extremely high impact). A = highest weight (i.e., 7), N = total number of respondents, MS =mean score, and RII is relative importance index. Based on Equation two, the attributes were calculated using their respective RII values and ranked accordingly, as shown in Table 3.

Table 3: Relative importance index Ranking of Attributes

| Attributes | Mean | Standard deviation | RII | Rank |
| --- | --- | --- | --- | --- |
| F1VAR46 | 5.7368 | 1.24838 | 0.819543 | 2 |
| F1VAR50 | 5.3772 | 1.33297 | 0.768171 | 13 |
| F1VAR44 | 5.5752 | 1.28734 | 0.796457 | 5 |
| F1VAR47 | 5.5263 | 1.31169 | 0.789471 | 7 |
| F1VAR45 | 5.5045 | 1.40048 | 0.786357 | 8 |
| F1VAR43 | 5.3604 | 1.41930 | 0.765771 | 15 |
| F1VAR39 | 5.193 | 1.44441 | 0.741857 | 26 |
| F1VAR38 | 5.2435 | 1.49614 | 0.749071 | 24 |
| F1VAR40 | 5.3478 | 1.41448 | 0.763971 | 17 |
| F2VAR60 | 5.2373 | 1.61021 | 0.748186 | 25 |
| F2VAR28 | 5.3017 | 1.58920 | 0.757386 | 20 |
| F2VAR70 | 5.2966 | 1.40396 | 0.756657 | 22 |
| F2VAR26 | 5.3879 | 1.34340 | 0.7697 | 12 |
| F2VAR25 | 5.3421 | 1.46238 | 0.763157 | 18 |
| F2VAR30 | 5.4741 | 1.34139 | 0.782014 | 10 |
| F2VAR24 | 5.3621 | 1.47676 | 0.766014 | 14 |
| F3VAR14 | 5.2735 | 1.45995 | 0.753357 | 23 |
| F3VAR13 | 4.8205 | 1.81286 | 0.688643 | 28 |
| F3VAR17 | 4.931 | 1.70791 | 0.704429 | 27 |
| F3VAR18 | 4.708 | 1.77121 | 0.672571 | 29 |
| F3VAR15 | 5.307 | 1.44594 | 0.758143 | 19 |
| F4VAR16 | 5.487 | 1.40404 | 0.783857 | 9 |
| F4VAR27 | 5.7434 | 1.20103 | 0.820486 | 1 |
| F4VAR29 | 5.3017 | 1.36554 | 0.757386 | 20 |
| F4VAR20 | 5.5304 | 1.48278 | 0.790057 | 6 |
| F5VART2 | 5.5847 | 1.24259 | 0.797814 | 4 |
| F5VAR31 | 5.359 | 1.44712 | 0.765571 | 16 |
| F5VAR32 | 5.4359 | 1.50508 | 0.776557 | 11 |
| F5VAR33 | 5.6154 | 1.27202 | 0.8022 | 3 |

RII provides a standardized measure that allows for the direct comparison and ranking of factors, with higher RII values indicating greater perceived importance among respondents.

Step 6: Exploratory Factor Analysis:- Factor analysis is a statistical technique used to reduce a large set of variables into a smaller set of underlying factors (Hair et al., 2006). In this study, the factors were extracted using principal component analysis (PCA), and the Kaiser–Meyer–Olkin (KMO) measure was used to assess sampling adequacy. KMO values between 0.8 and 1.0 indicate adequate sampling, whereas values below 0.5 are considered unacceptable. A higher KMO value indicates stronger correlations among the variables. The KMO value for the sample of risk mitigation attributes was 0.874, while the chi-square value of Bartlett’s test of sphericity was 3053.646, with an associated significance level of p = 0.000. The significance level was less than 0.001, satisfying the requirement for factor analysis. Furthermore, factor loadings greater than 0.5 were acceptable (Hair et al., 2006).

Figure 2 below highlights four key findings, as described below:

1. Five risk mitigation dimensions were identified by using factor analysis. The identified dimensions include Pre-project Planning, Project Monitoring and Controlling, Project-related, Inter-partner relationship, and Project management skills.

2. Variance explained by each dimension, for instance, Variance explained by dimension one(Pre-project Planning is 18.26%). Similarly, five dimensions are explained in a similar manner

3. Codes, for instance, code F2VAR28 indicates an adequate plan and specification in Table 1. Similarly, all codes below were explained in Table 1 in the above.

4. Factor loading values of each attribute, for instance, the factor loading value of F2VAR28 is 0.819. Similarly, all attributes are explained in the same manner, and finally, the total Variance explained by the five dimensions is 72.011%

F5VART2

F1VAR46

F1VAR44

F1VAR47

F1VAR45

F5VAR31

F1VAR40

F2VAR30

F4VAR29

F5VAR33

F5VAR32

F1VAR39

F1VAR43

F1VAR50

13.75%

Factor3: Project Related factors

F4VAR27

Factor4: Inter-partner relationship

13.70%

Facor5: Project management skills

F1VAR38

9.67%

Variance explained

dimensions

Figure 2:  Principal Components identified by Exploratory Factor Analysis

Factor1: Pre-project Planning

18.26%

F2VAR28

F2VAR60

F2VAR26

F2VAR70

F2VAR25

F2VAR24

F3VAR17

F3VAR14

F3VAR18

F4VAR16

F3VAR15

F3VAR13

F4VAR20

16.62%

Factor2: Project Monitoring and controlling

Dimensions

Variance explained

Factor Loading

Variance explained

0.819

0.817

0.742

0.723

0.707

0.651

0.807

0.772

0.770

0.754

0.743

0.708

0.538

0.846

0.810

0.643

0.634

0.587

0.694

0.685

0.628

0.625

0.587

0.582

0.560

0.794

0.593

0.573

0.564

4. Results and Discussion

The literature review was conducted as the first step in the study process to identify attributes for the public construction project. 29 attributes identified from the literature and a pilot survey were discussed in step 1. The relative importance index is employed in this study to determine the relative significance of various attributes influencing public construction projects. Based on the computed RII values, the top five attributes identified are as follows: on-time decision-making; ensuring construction teams have the necessary qualifications, abilities, and experience; solving disputes efficiently; transparent procurement and a competitive tendering process; and Audit norms, as explained in step 5. Based on factor analysis results, the names assigned to the dimensions in Figure 2 are discussed in the following paragraphs.

Factor 1: Pre-project Planning:- This dimension  contains six attributes, accounting for 18.26% of the total variance. The attributes within this factor primarily indicate adequate planning and specifications, a detailed feasibility study before starting the project, Stakeholder engagement in projects, defining clear responsibilities in the contract, and allocating contingency for uncertainties. These attributes are used to minimize risk in construction projects.

Factor 2: Project Monitoring and Controlling:- This dimension  comprises seven aspects, accounting for 16.62% of the total variance. Each attributes concerns characteristics of the project, including visiting the site regularly; regular quality control and quality assurance activities; adequate communication among all project participants; regular monitoring and feedback by top management; a clear reporting system; and Regular project updates. The explained attributes were used to minimize risk in construction projects.

Factor3: Project-related factors:-This dimension  comprises five attributes, accounting for 13.75% of the total variance. As illustrated in Figure 2, the attributes in the group include transparent procurement and a competitive tendering process, ensuring construction teams have the necessary qualifications, abilities, and experience; audit norms; availability of resources; and Timely land acquisition and appropriate compensation. Integrating all the explained attributes into public construction helps minimize risks.

Factor 4: Inter-partner relationship:-This dimension associated with seven attributes: good coordination among project participants, flow of information among parties, use of new technological approaches, Clients’ active enrollment and support, efficient dispute resolution, adequacy of planning and control techniques, and on-time decision-making. Accounting for 13.70% of the total variance, all attributes explained by this group are used to minimize risk in public construction projects.

Factor5: Project management skills:-This dimension comprises four attributes, accounting for 9.67% of the total variance, as explained in Figure 2. The attributes in this factor include project manager competency, Commitment of all project participants, appropriate risk allocation and risk-sharing, and owners’ competency. All of these are important factors for minimizing risk in public construction projects.

Overall Findings: From a governance perspective, there is a need for clear accountability, transparent decision-making, effective monitoring, and timely resolution of issues in construction projects. From a procurement point of view, ensuring transparent procurement and a competitive tendering process, improving the clarity of contractual requirements, and enhancing the efficiency of procurement processes. From a project-management perspective, project managers and other stakeholders should focus on timely decision-making, measuring project progress, project updating, effective communication, and systematic risk-response planning throughout the project life cycle. The overall finding provides a practical basis for Ethiopian public construction organizations to focus on high-priority risk mitigation measures and the five key dimensions of risk mitigation. This will improve risk management practices and project performance.

5. Conclusions

Twenty-nine attributes were identified based on literature and a pilot survey. The relative importance index and factor analysis were employed in this study to determine the relative significance of various attributes influencing public construction project risk mitigation. Using the relative importance index the top five attributes identified were on-time decision-making, ensuring construction teams have the necessary qualifications, abilities, and experience, solving disputes efficiently, Transparent procurement and a competitive tendering process, and Audit norms and  five risk mitigation dimensions were identified by using factor analysis: Pre-project Planning, Project Monitoring and Controlling, Project-related factors, Inter-partner relationship, and Project management skills.

Limitations & Scope of Future Work: While this study suggests useful insights into risk mitigation measures influencing the implementation of public construction projects in Ethiopia, it is important to acknowledge its limitations. First, the study focuses on attribute identification, ranking, and factor analysis. The study is not focused on how risk mitigation measures influence various project performance criteria, including schedule, cost, quality, safety, and modeling development. Second, the five dimensions were identified through factor analysis. However, the identified dimensions were not validated using complementary validation techniques. Third, limited in geographical scope. Future research should therefore broaden the geographical scope and incorporate a more diverse range of stakeholder groups.

REFRENCES

- A Guide to the Project Management Body of Knowledge Third Edition (PMBOK ® Guide). (2004).

- Ababa, A. (2011). The Federal Democratic Republic of Ethiopia Ministry of Finance and Economic Development Public Procurement and Property Administration Agency PUBLIC PROCUREMENT MANUAL.

- Acolin, A., Green, R., & Hoek-Smit, M. (2021). A ladder up the role of the construction sector in creating jobs and rebuilding emerging market economies.

- Alhammadi, Y., Radzi, A. R., & Rahman, R. A. (2025). Causes of Disputes in Construction: A Fuzzy Synthetic Evaluation. Journal of Engineering, Project, and Production Management.

- Aragaw, B. T., & Cherkos, F. D. (2025). Integrating Key Elements for Smooth Project Execution: Unveiling the Interplay of Critical Success Factors in High-Rise Construction. Journal of Legal Affairs and Dispute Resolution in Engineering and Construction, 17(2). https://doi.org/10.1061/jladah.ladr-1152

- Bakr, G. A. (2018). Ranking the factors that influence the construction project success: The Jordanian perspective. International Journal of Engineering and Technology

- Belihu, K. T., Woldesenbet, A. K., Shiferaw, A. T., Wubet, W. A., Yehualaw, M. D., & Taffese, W. Z. (2026). Cost Risk Factors in Construction Projects: A Contractor’s Perspective. Information (Switzerland).

- Chan, D. W. M., & Kumaraswamy, M. M. (1997). A comparative study of causes of time overruns in Hong Kong construction projects. In International Journal of Project Management (Vol. 15, Number 1).

- Chandra, H. P. (2015). Structural equation model for investigating risk factors affecting project success in Surabaya. Procedia Engineering, 125, 53–59. https://doi.org/10.1016/j.proeng.2015.11.009

- Cheng, M. Y., & Darsa, M. H. (2021). Construction schedule risk assessment and management strategy for foreign general contractors working in the Ethiopian construction industry. Sustainability (Switzerland).

- Cherkos, F. D., & Asfaw, F. A. (2025). Exploring the Interplay between Risk Management and Construction Risks: Implications for Project Performance through Structural Equation Modeling. Journal of Legal Affairs and Dispute Resolution in Engineering and Construction, 17(3). https://doi.org/10.1061/jladah.ladr-1218

- COCHRAN, W. G.  (1977). Sampling techniques. Wiley.

- Dessa, A. (2003). CLAIMS IN ETHIOPIAN CONSTRUCTION INDUSTRY.

- Dinku, A., & Kahssay, G. (2003). CLAIMS IN INTERNATIONAL CONSTRUCTION PROJECTS IN ETHIOPIA and CASE STUDIES ON SELECTED PROJECTS.

- Endris Yadeta, A. (2020). CRITICAL RISKS IN CONSTRUCTION PROJECTS IN ETHIOPIA. In International Journal of Civil Engineering, Construction and Estate Management (Vol. 8, Number 3).

- Fathi, M. (2024). A Structural Equation Model on Critical Risk and Success in Public–Private Partnership: Exploratory Study. Journal of Risk and Financial Management, 17(8). https://doi.org/10.3390/jrfm17080354

- Ferede, Y. S., Mashwama, N. X., & Thwala, W. D. (2021). Strategies to improve risk management in construction industries. Proceedings of International Structural Engineering and Construction.

- Garg, S., & Misra, S. (2021). Causal model for rework in building construction for developing countries. Journal of Building Engineering, 43. https://doi.org/10.1016/j.jobe.2021.103180

- Gouda Mohamed, A., Helmy Ammar, M., & Nabawy, M. (2023). Risks assessment using structural equation modeling: mega housing projects construction in Egypt. International Journal of Construction Management.

- Gupta, T., Kothari, C., & Misra, S. (2025). Integrating ‘Difficulty in Management as a decision-making criterion in the risk assessment of PPP infrastructure projects. Construction Management and Economics.

- Hair, J. F., Black, W. C., Babin, B. J., & Anderson, R. E. (2019). MULTIVARIATE DATA ANALYSIS EIGHTH EDITION. www.cengage.com/highered

- Hair, J., Black, W., Babin, B., Anderson, R. and Tatham, R. 2006.” Multivariate Data Analysis. 6th Edition, Pearson Prentice Hall.” Upper Saddle River.

- Hoque, M. I., & Hasan, M. (2025). Factors affecting the construction quality in Bangladesh. International Journal of Building Pathology and Adaptation, 43(3), 321–337. https://doi.org/10.1108/IJBPA-03-2022-0037

- Kineber, A. F., Othman, I., Oke, A. E., Chileshe, N., & Zayed, T. (2024). Modeling the relationship between value management implementation phases, critical success factors and overall project success. Construction Innovation.

- Kivrak, S., & Udan, O. H. (2023). Risk Management Practices in Ethiopian Somali Regional State Construction Projects. Buildings, 13(12). https://doi.org/10.3390/buildings13123130

- Koshe, W., & Jha, K. N. (2016). Investigating Causes of Construction Delay in Ethiopian Construction Industries. Journal of Civil, Construction and Environmental Engineering.

- Lin, C. L., & Chen, B. K. (2021). Research for risk management of construction projects in Taiwan. Sustainability (Switzerland), 13(4), 1–15. https://doi.org/10.3390/su13042034

- Maddah, R., Tripathi, K. K., & Jha, K. N. (2026). Risk Factors Affecting the Cost Performance of International Construction Projects. Journal of Legal Affairs and Dispute Resolution in Engineering and Construction.

- Shibani, A., Hasan, D., Saaifan, J., Sabboubeh, H., Eltaip, M., Saidani, M., & Gherbal, N. (2024). Financial risk management in construction projects. Journal of King Saud University - Engineering Sciences

- Sikhupelo, C., & Amoah, C. (2025). Barriers to the implementation of risk management practices for public infrastructure projects. Journal of Financial Management of Property and Construction.

- Sinesilassie, E. G., Tabish, S. Z. S., & Jha, K. N. (2018). Critical factors affecting cost performance: a case of Ethiopian public construction projects. International Journal of Construction Management.

- Szymański, P. (2017). Risk management in construction projects. Procedia Engineering.

- Tabish, S. Z. S., & Jha, K. N. (2012). Success Traits for a Construction Project. Journal of Construction Engineering and Management, 138(10), 1131–1138. https://doi.org/10.1061/(asce)co.1943-7862.0000538

- Tabish, S. Z. S., & Jha, K. N. (2018). Beyond the Iron Triangle in Public Construction Projects. Journal of Construction Engineering and Management, 144(8). https://doi.org/10.1061/(asce)co.1943-7862.0001517

- Tadesse, S., & Israel, D. (2016). Occupational injuries among building construction workers in Addis Ababa, Ethiopia. Journal of Occupational Medicine and Toxicology.

- Tang, W., Qiang, M., Duffield, C. F., David, Young, M., & Lu, Y. (2007). Risk Management in the Chinese Construction Industry. https://doi.org/10.1061/ASCE0733-93642007133:12944

- Tessema, A. T., Alene, G. A., & Wolelaw, N. M. (2022). Assessment of risk factors on construction projects in Gondar city, Ethiopia. Heliyon, 8(11). https://doi.org/10.1016/j.heliyon.2022.e11726

- Tripathi, K. K., & Jha, K. N. (2018). Determining Success Factors for a Construction Organization: A Structural Equation Modeling Approach. Journal of Management in Engineering.

- Viswanathan, S. K., Tripathi, K. K., & Jha, K. N. (2020). Influence of risk mitigation measures on international construction project success criteria–a survey of Indian experiences. Construction Management and Economics,

- Yang, S., Xiang, P., Wang, Y., Zhang, X., & Qian, Y. (2025). Emphasizing cross-regional matters: interpreting the critical risks of cross-regional mega infrastructure projects from an interactional perspective. Engineering, Construction and Architectural Management. https://doi.org/10.1108/ECAM-11-2024-1516

- Zegeye, Y. G., & Darsa, M. H. (2024). Potential risk factors affecting cost and schedule performance in the case of construction projects in Dire Dawa city administration and Harari region, Ethiopia. Building Engineering.