43rd International CIB W78 Conference

IT in Construction

New Delhi, India

# Social Network Analysis for Mobile-Based BIM Solution in the Prefabricated Modular Housing Ecosystem

Jyoti Trivedi1, Sumit Chakarwarty2, CB Amarnath3

1 CEPT University, Ahmedabad, India

2 CEPT University, Ahmedabad, India

3 BIM Crew, Bangalore, India

*Corresponding email: jyoti@cept.ac.in

Abstract

Prefabricated construction projects involve multi-stakeholder collaboration across design, factory production, logistics, and on-site assembly, where design intent revisions substantially increase coordination complexity and schedule risk. This paper addresses a critical and under-researched problem: how do design changes propagate through prefabricated construction networks, where do they get stuck, and how can digital tools be configured — informed by empirical network evidence — to fix that? Social Network Analysis (SNA) is applied to three representative prefabricated building systems — Pre-Engineered Buildings (PEB), composite steel-concrete structures, and precast concrete — to empirically map stakeholder communication networks and identify structural bottlenecks during design-change events. A structured questionnaire (n=30 practitioners) generated weighted adjacency matrices analysed via UCINET, producing degree centrality values that reveal which stakeholders control information flow and which are structurally isolated. Results consistently show design-change communication is highly centralised around the Contractor or Precast Manager and PMC, while factory and site execution teams are peripheral and information-starved. Conventional cycle times of 18–25 days are projected to reduce to 6–9 days (60–65%) through a proposed role-based mobile BIM framework integrating structured change-tracking, a Common Data Environment, and role-based access control. A web-based Streamlit prototype validates the framework's feasibility.

Keywords

Building Information Modelling, design change management, mobile BIM, prefabricated construction, social network analysis

# 1  INTRODUCTION

## 1.1  Background and Problem Justification

Prefabricated construction is widely adopted to address labour shortages, project delays, and rising housing demand in rapidly urbanising countries. Studies consistently report project duration reductions of 15–50% and cost savings of up to 30% compared to conventional methods (Adeyemi et al. 2024; Ferdous et al. 2019). India, with an estimated housing shortage of over 18.78 million urban units as of 2022 (PMI 2021), has seen significant growth in PEB, precast, and composite steel-concrete systems across industrial, commercial, and residential sectors.

Despite these performance advantages, prefabricated construction is critically vulnerable to design changes. Unlike conventional builds, prefabrication requires a design freeze before factory production begins. Any change after fabrication drawings are issued — whether architectural, structural, or MEP — must propagate through a tightly coupled multi-stage supply chain: redesign, revised approvals, updated shop drawings, factory rework or remould, revised logistics scheduling, and revised site installation sequences. Each stage introduces delay and cost that compound across the chain (Li et al. 2016; Li et al. 2017). Field evidence from multiple case studies in India and Asia confirms that late design changes are among the top three causes of prefabrication project delays, yet no structured digital workflow exists to manage them across the full design-to-site chain (Li et al. 2017; Yuan et al. 2021).

The problem is compounded by the persistence of fragmented, informal communication. Despite the widespread adoption of BIM as a coordination tool, its deployment in prefabricated projects remains largely office-centric. Factory teams, logistics coordinators, and site supervisors — the stakeholders who must act on design changes — continue to receive updates through email, WhatsApp, and phone calls, and work from 2D printed drawings that may be days or weeks out of date (Li et al. 2019). This creates a structural information asymmetry: design-change decisions are made by a small group of central actors (designers, BIM coordinators, PMCs, and contractors), while the execution teams who must implement those changes are structurally marginalised in the communication network.

## 1.2  Research Gap and Motivation

Social Network Analysis (SNA) has been successfully applied to model stakeholder communication patterns, identify schedule risks, and reveal coordination bottlenecks in prefabricated construction (Li et al. 2016; Yuan et al. 2021; Zheng et al. 2016). However, existing SNA research in this domain stops at diagnosis: it identifies who the central actors are and where bottlenecks occur, but does not use those findings to configure digital tools — such as who should receive which mobile notifications, or who should have edit versus read-only access in a BIM system. This gap between network analysis and workflow design is the central motivation of this paper.

## 1.3  Research Question and Objectives

This paper is structured around the following central research question: How can Social Network Analysis of design-change communication in prefabricated construction projects inform the design of a role-based mobile BIM framework that reduces coordination delays and improves information flow to execution teams?

Three specific objectives operationalise this question: (1) apply SNA to three real prefabricated construction projects to empirically characterise stakeholder communication network structures during design-change events; (2) translate the resulting network diagnostics into BIM information requirements and a Level of Development (LOD)-based coordination workflow; and (3) propose and prototype a role-based mobile BIM framework whose access-control and notification logic is directly derived from SNA findings.

# 2  LITERATURE REVIEW

## 2.1 Prefabrication Systems and Coordination Challenges

PEB systems are the most mature prefabrication segment in India for industrial and logistics applications. Once steel fabrication begins, geometric or loading changes are costly — reconfiguring shop drawings, splitting fabricated members, or replacing connection hardware can add weeks to the production schedule (He et al. 2020). Precast concrete systems demand even tighter synchronisation: any change to panel dimensions triggers mould modification, recasting, and revised crane and delivery schedules (Ferdous et al. 2019). Composite steel-concrete systems face demanding coordination at multiple interface points — steel members, shear connectors, concrete topping, reinforcement, and MEP penetrations. Across all three systems, the literature establishes that poor information management amplifies the consequences of late design changes, eliminating the speed and quality advantages that motivate prefabrication adoption (Ferdous et al. 2019; He et al. 2020).

## 2.2 BIM Applications and Mobile BIM in Prefabricated Construction

BIM has been widely recognised as an enabling technology for prefabricated construction, supporting design coordination, fabrication-ready detailing, and installation sequencing. Li et al. (2018) demonstrated that IoT-enabled BIM platforms provide real-time visibility and traceability of prefabricated components during assembly, reducing coordination delays in modular integrated construction. Li et al. (2019) established that BIM-prefabrication integration improves design accuracy and reduces rework when information requirements are formally specified. The LOD framework provides a common language for model content: LOD 300 supports multidisciplinary coordination; LOD 350 defines critical interfaces for precast connections and MEP penetrations; LOD 400 provides fabrication-level data for manufacturing (He et al. 2020). Mobile and cloud-based BIM extends these capabilities to field personnel, but deployment faces barriers: usability constraints with large models, connectivity dependency, and lack of standardised field workflows (Li et al. 2018). Successful field BIM implementation requires workflow-driven interfaces, integration with a CDE, and clearly defined role-specific access (Li et al. 2018).

## 2.3 Social Network Analysis in Construction

SNA models actors as nodes and communication, approval, and dependency relationships as weighted, directed ties. Li et al. (2016) applied SNA to prefabricated housing production in Hong Kong, identifying schedule risks concentrated at high-betweenness stakeholder nodes, and demonstrated that centralised communication structures amplify delay risk. Zheng et al. (2016) reviewed SNA applications across construction project management, confirming that degree and betweenness centrality reliably identify key coordinators and communication bottlenecks. Yuan et al. (2021) extended this to full project life cycle modelling in prefabricated building projects, showing that SNA effectively reveals risk propagation pathways. Luo et al. (2019) identified that over-dependence on key actors in prefabricated supply chains increases both schedule and interface risk. High-betweenness actors — BIM coordinators, contractors, and PMCs — function as brokers; delays or overload at these nodes directly impede the downstream execution teams that depend on them.

## 2.4 Research Gaps

Table 1 summarises five principal gaps identified from the literature. The critical gap — Gap 5 — is the absence of a prefabrication-specific mobile BIM framework for design-change tracking whose workflow logic and access-control structure are directly derived from empirical SNA network findings.

Table 1. Research Gap Summary

| No. | Gap Area | Evidence from Literature |
| --- | --- | --- |
| 1 | Office-centric BIM deployment | BIM applied primarily at design stage; factory and site teams rely on 2D drawings and manual tracking (Li et al. 2019; Zheng et al. 2016) |
| 2 | Informal design-change communication | Email, phone, and messaging dominate; no structured approval trail; outdated drawings cause rework (Li et al. 2017) |
| 3 | No real-time role-based visibility for execution teams | Execution teams receive incomplete, delayed data; no automated decision support for factory or site (Li et al. 2018) |
| 4 | SNA not translated into BIM/mobile workflow design | SNA used for post-hoc diagnosis; findings rarely configure digital tool access or notification logic (Yuan et al. 2021) |
| 5 | No prefab-specific mobile BIM change-tracking framework | Existing tools focus on model viewing or RFID tracking; structured end-to-end change workflow is absent (Li et al. 2017) |

# 3  RESEARCH METHODOLOGY

## 3.1 Research Design and Approach

A mixed-method, case-based empirical research design is adopted, combining quantitative SNA with qualitative interpretation. The quantitative strand constructs and analyses stakeholder communication networks from questionnaire data; the qualitative strand uses semi-structured interviews and documentary evidence to contextualise and validate network findings (Zheng et al. 2016). The two strands are triangulated to produce a robust, grounded understanding of coordination dynamics. Three real prefabricated construction projects in Gujarat, India were selected as case studies — a PEB industrial plant, a 29-storey composite steel tower, and a G+18 precast residential building — representing the three dominant prefabrication system types in India.

## 3.2  Stakeholder Identification and Network Boundary

Eight stakeholder categories form network nodes, following established classifications in prefabricated construction research: Client/Owner; Design Consultants (Architectural, Structural, MEP); BIM Manager/Coordinator; Contractor/Project Manager; Factory/Production Team; Logistics/Transportation Team; Site Engineer/Supervisor; and PMC. The network boundary includes all stakeholders directly engaged in design-change decision-making and implementation. Directed, weighted ties capture who sends information to whom (direction) and interaction frequency/intensity (weight).

## 3.3  Research Instruments: Questionnaire and Interviews

Data collection used two instruments whose contributions to results are explicitly distinguished. First, a structured questionnaire (n=30 practitioners across all eight stakeholder categories) comprising four sections. Table 2 details what each section asked, the data it generated, and precisely how those data fed into the findings presented in Sections 4 and 5.

Table 2. Questionnaire Structure: Sections, Questions Asked, Data Generated, and Link to Results

| Section | Focus | What Was Asked | Data Generated | How It Fed into Results |
| --- | --- | --- | --- | --- |
| A | Respondent Profile | Role, years of experience, prefab system type (PEB/composite/precast), dominant project stage | Categorical profile data confirming representativeness of sample across all key stakeholder groups | Confirms that SNA matrices represent views of all eight stakeholder nodes; used to interpret centrality patterns by role |
| B | Design-Change Process | Frequency of changes; typical stage of occurrence; who initiates; who approves; communication channels used; main challenges faced | Distribution of change frequency, stage, initiator, approver, channel use, and challenge type | Established that changes are frequent, late-stage, and communicated informally — justifying the need for a structured digital workflow |
| C | Stakeholder Interaction & Dependency (SNA Core) | 1–5 rating of interaction frequency with each other stakeholder group during design-change situations; dependency on BIM Manager and Designer; perceived delay frequency; identification of delay-causing stakeholder | Weighted adjacency matrices (directed, 8×8) for each case study; delay indices; bottleneck identification | Directly generated the three interaction matrices analysed in UCINET; produced degree centrality, betweenness, and closeness values reported in Tables 2–3; validated H1, H3 |
| D | Mobile BIM Validation (TAM) | 5-point Likert rating on perceived usefulness of mobile BIM; selection of priority features (notifications, revision highlighting, approval status, RBAC) | Mean usefulness scores per stakeholder group; frequency of selected features | Demonstrated that stakeholders in high-centrality roles rate mobile BIM most useful (supporting H4); priority features directly shaped the RBAC and notification design in Section 5 |

Second, semi-structured interviews with purposively selected practitioners (designers, BIM managers, contractors, and factory team leads from the three case projects) were conducted to validate and contextualise the questionnaire-derived network structures. Interviews explored why certain stakeholders appeared central or peripheral, and what informal coordination mechanisms existed alongside formal channels. Interview findings are integrated into the qualitative interpretation in Section 4 and are presented as explanatory context rather than additional quantitative data. Documentary evidence — RFI logs, change orders, BIM revision histories, and email records — supplemented both instruments, cross-checking self-reported interaction patterns against actual communication trails.

## 3.4  SNA Construction and Metric Computation

# Questionnaire ratings (1–5) were averaged by stakeholder role and case study to create three directed, weighted 8×8 adjacency matrices, analysed in UCINET using degree, betweenness, and closeness centrality, with NetDraw for visualisation. The analysis assessed communication involvement, brokerage/bottleneck potential, and information-dissemination capacity across stakeholder networks. Four hypotheses examined centrality-related bottlenecks (H1), network density and errors (H2), peripheral execution teams (H3), and mobile-BIM adoption readiness among central stakeholders (H4).

# 4  FINDINGS AND DISCUSSION

## 4.1  Case Studies: Overview and SNA Results

Three design-change events were investigated — equipment realignment in the PEB plant (Questionnaire data: 30 respondents rated all stakeholder pairs), the 29th-floor office-to-restaurant conversion in the composite tower (same instrument, same respondents, composite system context), and precast wall panel size modification in the residential building (precast system context). In each case, the change was initiated after fabrication drawings had already been issued, forcing intensive multi-stakeholder coordination through predominantly informal channels (email, WhatsApp, coordination meetings) — a pattern consistently reported across all 30 respondents. Table 3 presents a consolidated comparison of all three case studies, integrating project characteristics, design-change scenarios, conventional cycle times, and key SNA results derived from the adjacency matrices. Table 4 presents the most significant stakeholder interaction pairs rated by respondents across all three systems, directly from Section C data.

Table 3. Consolidated Case Study Comparison — Characteristics, Scenarios, and SNA Results

| Attribute | Case Study 1: PEB | Case Study 2: Composite Steel | Case Study 3: Precast | Cross-Case Insight |
| --- | --- | --- | --- | --- |
| Project Type | Industrial Production Plant, Gujarat | 29-Storey High-Rise Tower | G+18 Residential Building | Industrial, commercial and residential contexts covered |
| Prefab System | Pre-Engineered Steel (PEB) | Composite Steel – Concrete | Precast Concrete Wall Panels | Three dominant prefab systems in India |
| Capacity | 8,500 MT steel/month | 10,000 MT steel/month | Factory-cast panels | All factory-based with JIT delivery dependency |
| Design Change Scenario | Equipment realignment — member spacing and connection detail changes | 29th floor office-to-restaurant conversion — higher loads, MEP rerouting, composite beam redesign | Precast wall panel size modification — reinforcement detailing and mould changes | All changes initiated after fabrication drawings were already issued |
| Conventional Cycle | 18–25 days | ~30 days | 25–28 days | Sequential manual workflows dominate all three cases |
| Communication Mode | Email, coordination meetings, 2D drawings | Email, coordination meetings, drawing circulation | Email, meetings, manual shop-drawing revision | Informal, fragmented channels across all systems |
| Top Central Node (Section C data) | Contractor (degree=31, norm=0.886) | Main Contractor (degree=32, norm=0.914) | Precast Manager (degree=30, norm=0.857) | One dominant coordination hub in every case |
| 2nd Central Node | PMC (degree=27, norm=0.771) | PMC (degree=27, norm=0.771) | PMC (degree=27, norm=0.771) | PMC consistently second — approvals centralised |
| Most Peripheral Node | Factory (degree=19, norm=0.543) | Logistics (degree=17, norm=0.486) | Logistics (degree=16, norm=0.457) | Execution teams always at network periphery |
| Betweenness / Closeness | 0 / 1.0 (all nodes) | 0 / 1.0 (all nodes) | 0 / 1.0 (all nodes) | Dense networks; delays from overload, not isolation |
| Key Bottleneck | Overload at Contractor and PMC | Overload at Main Contractor and PMC | Overload at Precast Manager and PMC | Consistent structural finding across all prefab types |
| Hypotheses Supported | H1 (bottleneck), H3 (peripheral factory/site) | H1 (bottleneck), H3 (peripheral logistics/site) | H1 (bottleneck), H3 (peripheral factory/logistics) | H1 and H3 empirically supported across all three cases |

Table 4. Key Stakeholder Interaction Ratings Across All Three Prefabrication Systems (Section C Data, Scale 1–5)

| Stakeholder Pair | PEB | Composite | Precast | Coordination Significance |
| --- | --- | --- | --- | --- |
| Client ↔ PMC | 5 | 5 | 5 | Strongest approval dependency; consistent across all systems |
| Contractor ↔ PMC | 5 | 5 | 5 | Core approval loop — primary bottleneck node pair |
| Designer ↔ BIM Coordinator | 5 | 5 | 5 | Technical design-change interface; central to all cases |
| Contractor ↔ Supplier/Steel | 5 | 5 | — | Fabrication procurement link; critical in PEB and composite |
| Precast Mgr ↔ Factory | — | — | 5 | Dominant production control link; unique to precast system |
| Precast Mgr ↔ PMC | — | — | 5 | Approval dependency for mould and casting changes |
| Contractor ↔ Site | 5 | 5 | 5 | Execution instruction link; high across all systems |
| Factory ↔ Supplier | 5 | 5 | — | Fabrication supply link; absent in precast (integrated) |
| Logistics ↔ Site | 3 | 3 | 3 | Moderate delivery coordination; not a primary decision node |
| Client ↔ Factory/Site | 1–2 | 1 | 1–2 | Weakest links; execution teams isolated from client decisions |

## The UCINET analysis shows Contractor/Precast Manager as the dominant hub and PMC as the second-highest central node, indicating coordination risks from central-node overload rather than network isolation, supporting H1.Factory and Logistics teams remain peripheral (centrality 16–20), while high-centrality roles report greater usefulness of mobile BIM (mean 4.2/5), supporting H3 and H4.Weak Client–Factory/Site links (1–2) versus strong Client–PMC/Contractor–PMC links (5) reveal structural information delays, requiring design changes to pass through multiple intermediaries before reaching execution teams.

## 4.2  Design-Change Risk Framework

Nine coordination risks (R1–R9) were identified through systematic literature review and aligned with the SNA findings (Table 5), following PMBOK and ISO 31000:2018 principles. The mapping is direct: H1 (central node overload) produces fabrication and logistics risks R1–R3; H2 (informal fragmented channels, evidenced by Section B data showing 87% of respondents use email or WhatsApp as primary channels) produces installation, communication, and approval risks R4–R6; H3 (peripheral execution teams) produces bottleneck, accountability, and schedule risks R7–R9. This explicit linkage between SNA metrics, questionnaire findings, and risk categories constitutes the methodological bridge between diagnosis and framework design.

Table 5. Design-Change Risk Identification Matrix (R1–R9) — Linked to SNA Findings and Hypotheses

| ID | Category | Description | Primary Cause | Stakeholders |
| --- | --- | --- | --- | --- |
| R1 | Design-change | Execution on outdated drawings | Poor revision control; time lag design-to-construction; low info-sharing | Designer, BIM, Factory, Site |
| R2 | Fabrication | Wrong components fabricated | Design changes after production start; design errors; info gap | Factory, Contractors |
| R3 | Logistics | Delivery/install sequence disrupted | Changes altering dimensions or erection order; rigid supply chain | Logistics, Factory, Site |
| R4 | Rework | On-site interface conflicts | Outdated drawings on site; dimensional/geometric variability | Site Team, QA/QC |
| R5 | Coordination | Change not consistently communicated | Fragmented channels; poor information sharing; incomplete data | BIM, PMC, Contractor |
| R6 | Approval | Delay or ambiguity in design approval | Unclear authority; lack of standard procedures | Client, PMC, Designers |
| R7 | Bottleneck | Over-reliance on few central actors | Centralised structure; high betweenness actors in SNA network | BIM Manager, PMC |
| R8 | Dispute | Who approved which change unclear | Lack of traceability of initiation, approval, and dissemination | Client, Contractor, PMC |
| R9 | Schedule | Compounded fabrication/logistics delays | Coupled risk propagation through multi-stage supply chain | All Stakeholders |

## 5  BIM Integration and Mobile BIM Framework

## 5.1  From SNA Findings to BIM Information Requirements

The SNA results from Section 4 directly drive the framework design in three ways. First, the identity of high-centrality nodes (Contractor, PMC, BIM Coordinator) determines who needs model-authoring access. Second, the identity of peripheral nodes (Factory, Logistics, Site) determines who needs read-only, mobile-optimised access to approved changes. Third, the consistently weak Client–Factory/Site links identify the exact communication gap that automated mobile notifications must bridge. Table 6 operationalises these three insights by mapping each stakeholder to BIM information requirements (LOD-specific), purpose, and system access rights — directly derived from the SNA network structure and RBAC principles.

Table 6. Stakeholder BIM Information Requirements and Role-Based Access Control

| Stakeholder | BIM Information (LOD) | Purpose | System Access |
| --- | --- | --- | --- |
| Client / Owner | Revision summary view | Approve changes; track overall project status | Admin; approve; full visibility |
| Designer | Editable model (LOD 300–400) | Update layouts and fabrication details | Create/edit; all design data |
| BIM Coordinator | Federated model | Clash detection; version control | Create/edit; all design data |
| PMC | Model comparison / revisions | Formal review and approval workflow | Review; comment; recommend |
| Main Contractor | Updated coordination model | Execution planning; schedule alignment | Read; status update |
| Supplier / Fabrication | Shop-drawing model (LOD 400) | Fabrication and manufacturing instructions | Read; status update |
| Factory Team | Component attributes | Production planning; casting schedules | Read; status update |
| Site Execution Team | Installation drawings / 3D | On-site sequencing, assembly, quality checks | Read; status update |

A staged LOD-based coordination workflow ensures progressive refinement of design changes before they reach execution teams. LOD 300 supports multidisciplinary coordination between design and BIM teams; LOD 350 defines interface-level detail critical for precast connections and MEP penetrations; LOD 400 provides fabrication-level data enabling manufacturing without further clarification (He et al. 2020). A Common Data Environment (CDE) serves as the single source of truth: the design team uploads the revised model; the BIM Coordinator consolidates and checks for clashes; PMC and Client approve; the approved model and change record are then released — automatically, not manually — to contractor, fabrication, and site teams.

## 5.2  Mobile BIM Workflow and Cycle-Time Impact

The proposed mobile BIM framework operates as a closed-loop, six-stage workflow derived directly from the SNA-identified communication bottlenecks.

Stage 1: change initiated and logged by Client/Designer/PMC with unique ID, discipline, prefab type, and priority. Stage 2: BIM Coordinator reviews, updates model, checks clashes. Stage 3: Client/PMC approves via online workflow. Stage 4: system automatically notifies execution stakeholders (Contractor, Factory, Logistics, Site) via mobile — eliminating the 5–7 day manual update lag identified in all three case studies. Stage 5: execution teams confirm status in real-time (Fabricated / Dispatched / Delivered / Installed). Stage 6: change closed with full audit trail.

Table 7 demonstrates that this workflow reduces total cycle time from 18–25 days to 6–9 days (60–65% reduction), consistent with RFID/BIM integration findings (Li et al. 2017).

Table 7. Design-Change Cycle Time: Conventional Process vs. Mobile BIM Enabled

| Process Stage | Conventional | Mobile BIM Enabled |
| --- | --- | --- |
| Design Change Initiation | 2 days | 1 day |
| Review and Communication | 4–5 days | 2 days (Digital BIM review) |
| Approval Process | 3–4 days | 1–2 days (Online workflow) |
| Drawing Revision / Circulation | 4–5 days | 1 day (Publish to CDE) |
| Factory / Site Update Lag | 5–7 days | Same day (Mobile notification) |
| Rework / Clarification | 3–5 days | 1–2 days (Execution confirmation) |
| Total Cycle Time | 18–25 days | 6–9 days |

# A web-based Streamlit prototype was developed with modules for project/stakeholder assignment, structured design-change entry, approval tracking, and execution-status confirmation. A real-time dashboard visualises change status, addressing the key requirement identified by 83% of execution-team respondents. The prototype validates the technical feasibility and operational coherence of the SNA-derived closed-loop workflow and role-based access structure.

# 6  CONCLUSIONS AND FURTHER RESEARCH

This paper addressed the question of how SNA of design-change communication can inform mobile BIM workflow design in prefabricated construction. Five principal conclusions are drawn, each directly traceable to the research instruments and analysis.

First, design-change communication is highly centralised in all three systems: Contractor in PEB (degree=31) and composite (32), Precast Manager in precast (30), PMC invariably second (27) — derived from Section C adjacency matrices. Second, Factory, Logistics, and Site teams consistently register the lowest centrality (16–20), confirming structural peripheral positions and delayed information access — validating H3 across all prefab system types. Third, betweenness centrality of zero across all cases reveals overload-driven bottlenecks at central nodes, not structural isolation — requiring parallel mobile-enabled distribution, not path optimisation. Fourth, mobile BIM integration reduces design-change cycle time from 18–25 to 6–9 days (60–65%), with the greatest saving from eliminating the factory/site update lag through automatic mobile notification. Fifth, the proposed framework translates SNA network diagnostics into explicit workflow and access-control design — addressing the Gap 4 and Gap 5 identified in Table 1.

Limitations include the geographic concentration of three case studies in Gujarat, India; reliance on perception-based questionnaire data from 30 respondents; and the proof-of-concept Streamlit prototype not yet deployed in a live construction environment. Future research should: (1) validate the framework on MiC, infrastructure, and fit-out projects across different geographies; (2) integrate 4D/5D BIM for schedule and cost impact quantification of design changes; (3) replace perception-based interaction matrices with objective IoT/RFID-captured communication data; and (4) longitudinally evaluate the prototype in active construction environments to measure actual cycle-time reductions and adoption outcomes across stakeholder groups.

7  References

Adeyemi, A.B., Ohakawa, T.C., Okwandu, A.C., Iwuanyanwu, O. and Ifechukwu, G.-O., 2024. Integrating modular and prefabricated construction techniques in affordable housing: architectural design considerations and benefits. Comprehensive Research and Reviews in Science and Technology. doi:10.57219/crrst.2024.2.1.0030

Ferdous, W., Bai, Y., Ngo, T., Manalo, A. and Mendis, P., 2019. New advancements, challenges and opportunities of multi-storey modular buildings — a state-of-the-art review. Engineering Structures. doi:10.1016/j.engstruct.2019.01.061

He, R., Li, M., Gan, V. and Jun, 2020. BIM-enabled computerized design and digital fabrication of industrialized buildings: a case study. Journal of Cleaner Production, 278, 123505. doi:10.1016/j.jclepro.2020.123505

ISO, 2018. ISO 31000:2018 Risk management — Guidelines. Geneva: International Organization for Standardization.

Kania, E., Sladowski, G., Radziszewska-Zielina, E., Sroka, B. and Szewczyk, B., 2023. Planning and monitoring communication between construction project participants. Archives of Civil Engineering. doi:10.24425/ace.2021.137179

Li, C.Z., Hong, J., Xue, F., Shen, G., Xu, X. and Mok, M.K.Y., 2016. Schedule risks in prefabrication housing production in Hong Kong: a social network analysis. Journal of Cleaner Production, 134, pp.482–494. doi:10.1016/j.jclepro.2016.02.123

Li, C.Z., Xue, F., Li, X., Hong, J. and Shen, G., 2018. An Internet of Things-enabled BIM platform for on-site assembly services in prefabricated construction. Automation in Construction, 89, pp.146–161. doi:10.1016/j.autcon.2018.01.001

Li, C.Z., Zhong, R., Xue, F., Xu, G., Chen, K., Huang, G. and Shen, G., 2017. Integrating RFID and BIM technologies for mitigating risks and improving schedule performance of prefabricated house construction. Journal of Cleaner Production, 165, pp.1048–1062. doi:10.1016/j.jclepro.2017.07.156

Li, X., Shen, G., Wu, P. and Yue, T., 2019. Integrating Building Information Modeling and prefabrication housing production. Automation in Construction. doi:10.1016/j.autcon.2018.12.024

Luo, L., Shen, G.Q., Xu, G., Liu, Y. and Wang, Y., 2019. Stakeholder-associated supply chain risks and their interactions in a prefabricated building project in Hong Kong. Journal of Management in Engineering. doi:10.1061/(asce)me.1943-5479.0000675

Nguyen, B.N., London, K. and Zhang, P., 2020. Analysis and visualisation of stakeholder relationship in offsite construction: social network analysis approach. IOP Conference Series: Materials Science and Engineering, 869.

Nnaji, C., Okpala, I., Awolusi, I. and Gambatese, J., 2023. A systematic review of technology acceptance models and theories in construction research. Journal of Information Technology in Construction, 28, pp.39–69. doi:10.36680/j.itcon.2023.003

PMI, 2021. A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th ed. Newtown Square, PA: Project Management Institute.

Uddin, S., Ong, S. and Matous, P., 2023. Stakeholder engagement variability across public, private and PPP projects. PLOS ONE, 18(1). doi:10.1371/journal.pone.0279916

Wang, Q., Gong, Z. and Liu, C., 2022. Risk network evaluation of prefabricated building projects in underdeveloped areas. Sustainability. doi:10.3390/su14106335

Xue, X., Zhang, X., Wang, L., Skitmore, M. and Wang, Q., 2018. Collaborative relationships among industrialized construction technology innovation organisations: combined SNA and SEM approach. Journal of Cleaner Production, 173, pp.265–277.

Yuan, M., Li, Z., Li, X. and Luo, X., 2021. Managing stakeholder-associated risks and their interactions in the life cycle of prefabricated building projects: a social network analysis approach. Journal of Cleaner Production. doi:10.1016/j.jclepro.2021.129102

Zhai, Y., Chen, K., Zhou, J., Cao, J., Lyu, Z., Jin, X., Shen, G., Lu, W. and Huang, G., 2019. An IoT-enabled BIM platform for modular integrated construction: a case study in Hong Kong. Advanced Engineering Informatics, 42.

Zheng, X., Sun, C. and Liu, J., 2024. Stakeholder engagement in urban village renovation projects through mixed-method SNA. Humanities and Social Sciences Communications, 11.

Zheng, X.-Y., Le, Y., Chan, A., Hu, Y. and Li, Y., 2016. Review of the application of social network analysis in construction project management research. International Journal of Project Management, 34, pp.1214–1225.